## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2191-swen-04-1-The A Team
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | TB; October 22
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | TB; October 22
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | TB; October 22
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | TB; October 22
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | TB; October 22
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | TB; October 22
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | TB; October 22
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | RC; October 8th
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | RC; October 8th
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | RC; October 8th
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | RC; October 8th
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | RC; October 8th
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | RC; October 8th
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | RC; October 8th
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | RC; October 8th
As a Player I want to Sign-out so I can remove myself from the playerlobby and not play a game | Given I am siged in, when I click the signout button, I should be taken to Home screen and only see the number of users online and an option to sign back in. |  |  | Pass | TB; November 2
As a Player I want to be able to move my pieces to an empty diagonally adjacent black space so that I can advance my pieces. | Given that there is an adjacent black space occupied with my own piece when I try to make move my piece there then the game will not let me. |  |  | Pass | RC; November 1st
| Given that there is an empty black space diagonally adjacent to the piece I am selecting to move, when I move my piece to make that move then the game will let me and the move will be made |  |  | Pass | RC; November 1st
| Given that there is an opponent sitting directly diagonal to my piece and there is an empty space behind it when I move my piece to that space then their piece will be removed. |  |  | Pass | RC; November 1st
| Given it is my move, when I select one of my pieces then I should be able to drag it to an empty square |  |  | Pass | RC; November 1st
| Given it is not my turn, when I click on a piece then I should not be able to move it |  |  | Pass | RC; November 1st
As a Player, when I perform a valid hop over an opponent's piece, it should be "captured" and taken off of the board so that I can win the game. | Given the active player's selected piece is diagonally adjacent to an opponent's piece with an empty space diagonally behind it, when they move my piece to the empty square diagonally behind then the game should let me and the "jumped" piece should be removed from the board |  |  | Pass | RC; November 1st
| Given that the active player makes a legal capture when this move occurs then the moved piece should be placed on the empty square diagonally behind the captured piece |  |  | Pass | RC; November 1st
| Given that the active player makes a legal capture move, when this move is over then the captured piece should be taken off of the board |  |  | Pass | RC; November 1st
| Given the active player's piece is diagonally adjacent to an opponents piece, but the square behind this piece is occupied or non-existent (edge) when the active player attempts this capture then the game will not allow it. |  |  | Pass | RC; November 1st
As a Player I want to be able to get a king piece by having a single piece reach the row furthest from me so that my piece can move in both directions. | Given that I move a piece to my opponents first row when I make this move then the piece should be made a king |  |  |  |  | Pass | RC; November 6th
| Given I move my piece to the last row when this piece is made king then the piece model should be updated to a king's look |  |  |  |  | Pass | RC; November 6th
| Given I moved a white piece to the last row, when this move occurs, then it should become a white king. |  |  |  |  | Pass | RC; November 6th
| Given I moved a red piece to the last row, when this move occurs, then it should become a red king. |  |  |  |  | Pass | RC; November 6th
As a Player, I want to move a king in any diagonal direction 1 spot so that the gameplay follows the rules of American checkers. | Given the piece I selected to move is a king, when I move the piece to any diagonally adjacent spot that is not occupied then the game should let me. |  |  |  |  | Pass | RC; November 6th
| Given that I am moving a king, when I have the option to capture a piece diagonally adjacent from that king with an empty spot in that path, then the game will allow me to make this capture. |  |  |  |  | Pass | RC; November 6th
As a Player I want to be able to make a multiple jump move with the same piece by jumping from vacant dark square to vacant dark square in a single turn so that the opponent may have less pieces on the board. | Given the active player captures a piece and there is another legal capture immediately after when they make this move then they will be given the option to make that capture. |  |  |  |  | Pass | RC; November 6th
| Given the piece that captured an opponent is in a position to where there are two available captures when this happens then the player should be given the choice between either path. |  |  |  |  | Pass | RC; November 6th
| Given I am moving a regular piece (not king) when making a multiple jump move then only forward options are available |  |  |  |  | Pass | RC; November 6th
| Given I am moving a king when I make a multiple jump move to capture multiple pieces then both forwards and backwards options should be available. |  |  |  |  | Pass | RC; November 6th
As a Player I want to be able to resign from a game at any point so that the game may end. | Given the player is in the middle of playing a game when they press resign then the game should end and make the other player the automatic winner. |  |  | Pass | RC; November 1st
| Given that I am playing a game when the other player presses resign then I should be given a win screen and the option to exit to the home screen. |  |  | Pass | TB; November 24th
| Given it is not the current user's turn, when they press the resign button then they should be resigned and taken back to the home screen. |  |  | Pass | TB; November 24th
| Given I have just made a move that is awaiting validation, when this state is entered then the resign button should be disabled. |  |  | Pass | RC; November 1st
| Given the active color's player is in the "Empty Turn State" when they click the resign button then they should be taken back to the home page. |  |  | Pass | RC; November 1st
As a Player I want to capture ALL of my opponents pieces so that I can win the game of checkers | Given my opponent only has one piece left, when I capture it then I should win the game |  |  |  |  | Pass | RC; November 6th
As a spectator, when I click on someone's name who is currently in a game, I should be able to see and watch their game. | Given someone is in a game when I click on their name then I should join that match as a spectator |  |  |  |  | Pass | TB; November 24th
| Given I am spectator when I select any object on the board then nothing will happen. |  |  |  |  | Pass | TB; November 24th
| Given I am a spectator when I am viewing a game, then the only option present to me should be to exit the game. |  |  |  |  | Pass | TB; November 24th
As a Player I want to be able to play against a computer so that I can practice without the need for another player. | Given I want to play against an AI when I select this option, then I should be put into a game with a computer player |  |  |  |  | Pass | RS; November 24th
| Given that it is the AI Player's turn, when this occurs, then it should be able to make and submit moves |  |  |  |  | Pass | RS; November 24th
| Given that there are no other players in the lobby when I go to start a game, then the AI player should be available to play against |  |  |  |  | Pass | RS; November 24th
| Given the AI player is in a game, when a new user clicks on the AI, then a new AI player will be assigned to that user |  |  |  |  | Pass | RS; November 24th